## Projected
|  | 17th Nov | 2nd Dec | 28th Dec | 8th Jan | 15th Feb | 4th Mar | 27th Mar | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14
Report
Create an account
Load template
Read guidelines | bar: WK7 to WK12
Deliverables
Create GIT Account
Share with lecturer
Commit regularly | bar: WK9; WK12
Record prototype | bar: WK12
Upload VIVA | bar: WK12
Submit report | bar: WK12
Research Methodology
Hypothesis
Research Questions
Research Methods
Research Pipeline
Finalise section in report | bar: WK7
Literature Review
Review datasets
Review algorithms
Review evaluation metrics
Finalise section in report | bar: WK10 to WK12
Prototype
Find tutorial
Replicate tutorial
Create custom dataset
Tweek prototype | bar: WK7 to WK8
Generate evaluation results | bar: WK9 to WK10
Discussion of Results
Write prototype evaluation | bar: WK10 to WK11
Write dataset evaluation | bar: WK10 to WK11
Write hypothesis testing | bar: WK11 to WK12
Write project evaluation | bar: WK11 to WK12
Finalise section in report | bar: WK11 to WK12
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: WK12
Finalise Introduction | bar: WK12
Finalise Abstract | bar: WK12

## Actual
|  | 17th Nov | 2nd Dec | 28th Dec | 8th Jan | 15th Feb | 4th Mar | 27th Mar | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14
Report
Create an account
Load template
Read guidelines
Deliverables
Create GIT Account
Share with lecturer
Commit regularly
Record prototype
Upload VIVA
Submit report
Research Methodology
Hypothesis
Research Questions
Research Methods
Research Pipeline
Finalise section in report
Literature Review
Shaping of Literature Review
Software Defined Networks Review
DOS attacks Section
Types of DOS attacks Section
Defense Mechanisms Section
Different Techniques to Mitigate DOS attacks Section
Prototype
Find tutorial / Review existing games
Replicate tutorial
Create custom dataset / assets
| Develop prototype | [7 empty] | WK9: prototype required more time due to challenges arising
Generate evaluation results
Discussion of Results
Write prototype evaluation
Write dataset evaluation
Write hypothesis testing
Write project evaluation
Finalise section in report
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations
Finalise Introduction
Finalise Abstract